## Projecttracker
	Project AssetList, Anomaly		INSTELLINGEN	13 gamelab uren p/w	4 werkweken over	1 Polish week voor scene en presentatie		1D = 5P
				^52 uur total^		Alles moet hier af zijn, wordt niks nieuws gepland!
v	< O = Opermking, Zie meest rechtse balk
v						in punten		MoSCoW Method				?
	ProjectAssets	Categorie	Toegewezen aan	Geschat begin	Geschat einde	Geschatte hoeveelheid werk	SprintNmr.	Prioriteit	LEEG	Weeknummer	TrelloChecked	Implemented	Opmerkingen
	GameHandler	Script	Jan	28-11-2016	2-12-2016	12	0	Must Have		48	X
	Player_ComboScript	Script	Jan	28-11-2016	2-12-2016	6	0	Must Have
	HumanEnemy_00	3DModel	Niek	28-11-2016	2-12-2016	5	0	Must Have		48	X
	HumanEnemy_00	Texture	Niek	28-11-2016	2-12-2016	3	0	Must Have		48	X
	PlayerAttack_00	Animation	Niek	28-11-2016	2-12-2016	1	0	Must Have		48
	PlayerAttack_01	Animation	Niek	28-11-2016	2-12-2016	1	0	Must Have		48
	PlayerAttack_02	Animation	Niek	28-11-2016	2-12-2016	1	0	Must Have		48
	PlayerAttack_03	Animation	Niek	28-11-2016	2-12-2016	1	0	Must Have		48
	PlayerAttack_04	Animation	Niek	28-11-2016	2-12-2016	1	0	Must Have		48
	PlayerJump_00	Animation	Niek	28-11-2016	2-12-2016	1	0	Must Have
	CameraMovement	Script	Renzo	28-11-2016	2-12-2016	3	0	Must Have		48	X
	BossTokkie	3DModel	Sunray	28-11-2016	2-12-2016	4	0	Must Have
	BossTokkie	Rig	Sunray	28-11-2016	2-12-2016	1	0	Must Have
	BossTokkie	Texture	Sunray	28-11-2016	2-12-2016	3	0	Must Have
	MainChar	3DModel	Sunray	28-11-2016	2-12-2016	?	0	Must Have
	MainChar	Rig	Sunray	28-11-2016	2-12-2016	?	0	Must Have
	MainChar	Texture	Sunray	28-11-2016	2-12-2016	?	0	Must Have
	WeaponShortSword	3DModel	Sunray	28-11-2016	2-12-2016	1	0	Must Have
O	WeaponShortSword	Texture	Sunray	28-11-2016	2-12-2016	1	0	Must Have
	AnomalySFX_00	SoundFX
	AnomalySFX_01	SoundFX
	AnomalySFX_02	SoundFX
	AnomalySFX_03	SoundFX
	AnomalySFX_04	SoundFX
	AnomalySFX_05	SoundFX
O	AnomalySFX_06	SoundFX
	AnomalySFX_07	SoundFX
	AnomalySFX_08	SoundFX
	AnomalySFX_09	SoundFX
	Ashtray	Prop	Quinten			1	1	Would Have
	Axe	Prop	Matthijs			3	1	Should Have
	BackGroundAmbience	SoundFX
	Barn	Architecture	Aart-Jan			20	1	Must Have
	Barrel	Prop				1		Could Have
	Basement_CorkBoardWallmounted	Prop				1		Should Have
	Basement_Desk	Prop				4		Must Have
	Basement_Newspaper	Prop				1		Could Have
	Basement_Pipes	Architecture				2		Could Have
O	Basement_Staircase	Architecture				5		Must Have
	Bath	Prop				2		Could Have
	BearTrap	Prop				3		Should Have
O	Bed	Prop				5		Could Have
O	BeerBottle	Environmental				2		Could Have
	BicycleBell	Prop				2		Should Have
	Birds_Fladdering	SoundFX
O	BirdsSpooked	ParticleFX
O	BirdsSpooked	SoundFX
	Boiler	Environmental				10		Could Have
	Boltcutter	Prop				3		Should Have
	Book_Closed	Prop				1		Could Have
	Book_Open	Prop				2		Could Have
	Boots	Prop				2		Could Have
	Briefcase	Prop				3		Must Have
	Briefcase_Notes	Prop				2		Must Have
	Broom	Prop				1		Could Have					WitchesBroom
	CameraController	Script						Must Have
	Candle	Environmental				2		Should Have
	Cellphone	Prop				7		Must Have
	Cellphone_Broken	Prop				4		Should Have
	CellPhone_BuzzSFX	SoundFX
O	CellPhone_ChargingSFX	SoundFX
	CellPhone_RealLifeClock	Script
	CellPhone_ReskinnnerApp	Script
	Cellphone_Ringtone	SoundFX
	CellPhone_TouchSound	SoundFX
	CellphoneCharger_Deskmounted	Prop				4		Must Have
	Chain	Prop				1		Could Have
	Chair_00	Prop				3		Should Have
?	Chair_01	Prop				3		Could Have
O	Chandelier	Environmental				3		Could Have
	Character_Arms	Alive
	Character_Body	Alive
	CharacterAnimation_ArmsIdle	Animation
	CharacterAnimation_ArmsIdlePhone	Animation
	CharacterAnimation_ArmsRunning	Animation
	CharacterAnimation_ArmsWalking	Animation
	CharacterAnimation_ArmsWalking	Animation
	CharacterAnimation_Crouching	Animation
	CharacterAnimation_DeathByAlien	Animation
	CharacterAnimation_Insanity	Animation
	CharacterAnimation_Interact	Animation
	CharacterAnimation_Jumping	Animation
O	CharacterAnimation_Suicide	Animation
	CharacterAnimation_Suicide2	Animation
	ChickenCoop	Environmental				5		Should Have
O	Cleaver	Prop				4		Could Have
	Closet_wallmounted	Architecture				4		Should Have
	Clother_Shredded	Prop				5
	Clothes	Prop				4
	Coat Rack	Architecture				2
	ConfederateFlag	Environmental				1
	Container	Environmental				3
	CookingTimer	Prop				2
	Couch	Architecture				3
O	CraftingSystem	Script
	CraftMaterial_CarrBattery	Prop
	CraftMaterial_CarrBattery	Sprites
	CraftMaterial_CookingTimer	Prop
	CraftMaterial_CookingTimer	Sprites
	CraftMaterial_DuctTape	Prop
	CraftMaterial_DuctTape	Sprites
	CraftMaterial_Gasoline	Prop
	CraftMaterial_Gasoline	Sprites
	CraftMaterial_Nuts&Bolts	Prop
	CraftMaterial_Nuts&Bolts	Sprites
	CraftMaterial_Rope	Prop
	CraftMaterial_Rope	Sprites
O	CraftMaterial_ScrapMetal	Prop
	CraftMaterial_ScrapMetal	Sprites
	CraftMaterial_StartCables	Prop
	CraftMaterial_StartCables	Sprites
	CraftMaterial_WoodenPlanks	Prop
	CraftMaterial_WoodenPlanks	Sprites
	CraftRecipe_BearTrap	Prop
O	CraftRecipe_BearTrap	Sprites
	CraftRecipe_Generator	Prop
	CraftRecipe_Generator	Sprites
	CraftRecipe_Lantern	Prop
	CraftRecipe_Lantern	Sprites
	CraftRecipe_LockPick	Prop
	CraftRecipe_LockPick	Sprites
	CraftRecipe_MakeShiftAxe	Prop
	CraftRecipe_MakeShiftAxe	Sprites
	CraftRecipe_NoiseMaker	Prop
	CraftRecipe_NoiseMaker	Sprites
	Crate	Prop				1
	Curtains	Architecture				4
	Door_00	Architecture				2
	Door_01	Architecture				2
	DOSComputer	Prop				4
	Douche	Prop				2
	DrippingWater	SoundFX
	Duck_Evil	Alive				10
	Duck_Qwuack	SoundFX
	DuckTape	Prop				1
	EnemyBehaviour	Script
	EnemyBreathing	SoundFX
	EnemyFootsteps	SoundFX
	EnemyRoar00	SoundFX
	EnemyRoar01	SoundFX
	EnemyRustle_Bushes	Animation
	EnemyRustle_Bushes	SoundFX
	EnemyRustle_Trash	Animation
	EnemyRustle_Trash	SoundFX
	EnemyVision	Script
	EnemyWarCry	SoundFX											We hebben de Roar ook al
	FalloutShelter	Architecture				5
	FarmSign	Environmental				2
	Feathers	Nature				2
	Fence_Steel	Prop				2
	Fence_SteelBroken	Prop				3
	Fence_Wood	Prop				2
	Fence_WoodBroken	Prop				3
	Fireplace	Architecture				4
	Flashlight	Prop				2
	Flashlight	Script
	FlowerDead_00	Nature				4
	FlowerDead_01	Nature				4
	ForeGroundAmbience	SoundFX
	Freezer	Environmental				3
	Furnace	Environmental				3
	GameManger	Script
	Gasmask	Prop				6
	GlassShattered	Environmental				2
	Gramaphone_Tune	SoundFX
	Gramaphone_TuneWithScreeches	SoundFX
	GrandFatherClock_OnHourBong	SoundFX
	GrandFatherClock_Ticking	SoundFX
O	GUI	Script
	Hammer	Prop				2
O	HangingBodies	Environmental				4
	HanginRope	Environmental				3
	Hay	Environmental				1
	HorseHoof_Rusty	Prop				1
	House_Base	Architecture				30
	House_Room_00	Architecture				15
	House_Room_01	Architecture				15
	House_Room_02	Architecture				15
	House_Room_03	Architecture				15
	House_Room_04	Architecture				10
	House_Room_05	Architecture				10
	House_Room_06	Architecture				10
	House_Room_07	Architecture				10
	House_Room_08	Architecture				10
O	Insanity	Script
	Insanity_BloodPool	Shader				1
	Insanity_Bloodspatter	Sprites				1
	Insanity_DrippingBlood	Shader				1
	Insanity_Eyes	Prop				1
	Insanity_Fingers	Prop				2
	Insanity_PFX	ParticleFX				35							Moet nog uitbreiden hierop
	Insanity_Tentacles	Prop				3
O	InsanityUndertone	SoundFX
	Intro_CutScene	SoundFX
O	InventorySystem	Script
	Item(class)	Script
	ItemDatabase	Script
	Jerrycan	Environmental				3
	Jochem	Shader				69
	Kitchen_Closet	Architecture				3
	Kitchen_Sink	Architecture				4
	Kitchen_Table	Architecture				3
	Kitchen_Tools	Prop				5
	Ladder	Prop				2
	LadderBroken	Prop				2
	Lamp_Hanging	Architecture				4
	Lamp_Standing	Architecture				4
	Lamp_WallMounted	Architecture				2
	Lantern	Prop				4
	Light(class)	Script
	LightManager	Script
	LightSwitch	Architecture				1
	Lockpick	Prop				2
	LooneyTunes_Intro	Animation
	LooneyTunes_Intro	SoundFX
	Mailbox	Prop				3
	MainCharacter	Alive				12							Alleen armen, of make Human???
	MainEnemy	Alive				30							Heeft nog een naam nodig
	Mais_crops	Nature				10
	MapNotes	Sprites				3
	Newspaper	Prop				1
	NoiseMaker	Prop				5
	NoiseMaker	Script
	NoiseMaker_Charging	SoundFX
	NoiseMaker_InEffect	SoundFX
	Outhouse	Environmental				4
	Painting_00	Architecture				2
	Painting_01	Architecture				2
	Painting_02	Architecture				2
	Painting_03	Architecture				2
	Painting_04	Architecture				2
	PaperNotes	Prop				1
	Particle(class)	Script
	ParticleManager	Script
	Pencil	Prop				1
	PhoneUI	Sprites				20
	Piano	Prop				6
	PianoTune_00	SoundFX
	PianoTune_01	SoundFX
	Pitchfork	Prop				3
	Plank	Prop				1
	PlankBroken	Prop				1
	PlayerBreathing	ParticleFX
	PlayerBreathing	SoundFX
	PlayerController	Script
	PlayerCrouchFootsteps	SoundFX											Kunnen dit normale footsteps niet zijn? Perhaps slomer en gedempt ofso
	PlayerDeathcries	SoundFX
	PlayerFootsteps	ParticleFX
	PlayerFootsteps	SoundFX
	PlayerJumpLanding	ParticleFX
	PlayerJumpLanding	SoundFX
	PlayerPanicking	Animation
	PlayerPanicking	SoundFX
	Plowing_Wagon	Environmental				5
	PowerGenerator	Environmental				10
	Rake	Prop				2
	Rat	Environmental				5
	RatHole	Architecture				1
	Rats	SoundFX
	RatTrap	Environmental				2
	Ravens	SoundFX											Verschil van de vogels? - is deze overbodig?
	Rock_00	Environmental				2
	Rock_01	Environmental				2
	RockingChair	Prop				5
	Rope	Prop				3
	Rug	Environmental				4
	Rugsack	Prop				4
	Sadle	Prop				3
	Safe	Prop				3							Een kluis
	Saw	Prop				4
	ScrapMetal	Prop				3							Wordt ook een pick-up
	Screwdriver	Prop				2
	ScriptedEvents	Script
	Shotgun_Broken	Prop				7
	Sickle	Prop				3
	Sigars	Prop				1
	Silo	Architecture				7
	Sink	Prop				3
	Skybox	Script
	Skybox_00	Overig				3
	Skybox_01	Overig				3
	Skybox_02	Overig				3
	SoundManager	Script
	SqueakyDoor	SoundFX
	SqueekingWood	SoundFX
	Staircase	Prop				10
	StartCables	Prop				2							Wordt ook een pick-up
	SuitCaseNote	Prop
	Swing	Prop											Schommel
	Table	Prop				2
	Table_Small	Prop				2
	Telephone_Wallmounted	Prop				4
	TelephonePole	Prop				2
	TelevisionStatic	Shader
	Terrain	Environmental				15
	TimberBlocks	Prop				1
	Toilet	Prop				3
	Tom&Jerry_intro	SoundFX
	Toolbelt	Prop				2							Werdt dit ook gebruikt?
	Tractor	Environmental				20
	TractorAccu	Prop				2							Wordt ook een pick-up
	Trashcan	Prop				1
	Tree_00	Nature				1
	Tree_01	Nature				1
	Tree_02	Nature				1
	TreeStump	Nature				1
	Truck	Prop				20
	UISprite_Background01	Sprites
O	UISprite_Background02	Sprites
	UISprite_Background03	Sprites
	UISprite_Background04	Sprites
	UISprite_BarnPhoto	Sprites
	UISprite_BatteryStatus00	Sprites
	UISprite_BatteryStatus01	Sprites
	UISprite_BatteryStatus02	Sprites
	UISprite_DuckHunt	Sprites
	UISprite_FlashLigt	Sprites
	UISprite_Gallery	Sprites
	UISprite_GalleryFolders	Sprites
	UISprite_HeartMeter	Sprites
	UISprite_HousePhoto	Sprites
O	UISprite_KidOnSwing	Sprites
	UISprite_KidOnSwingHeadless	Sprites
	UISprite_MapApp	Sprites
O	UISprite_Notebook	Sprites
	UISprite_PhoneBackground	Sprites
	UISprite_Settings	Sprites
	UISprite_SuitCaseNote00	Sprites
	UISprite_SuitCaseNote01	Sprites
	UISprite_SuitCaseNote02	Sprites
	UISprite_SuitCaseNote03	Sprites
	UISprite_SuitCaseNote04	Sprites
	UISprite_SuitCaseNote05	Sprites
	UISprite_SuitCaseNote06	Sprites
	UISprite_SuitCaseNote07	Sprites
	UISprite_SuitCaseNote08	Sprites
	UISprite_SuitCaseNote09	Sprites
	UISprite_SuitCaseNote10	Sprites
	UISprite_SuitCaseNote11	Sprites
	UISprite_SuitCaseNote12	Sprites
	UISprite_SuitCaseNote13	Sprites
	UISprite_SuitCaseNote14	Sprites
	UISprite_TeamPhoto00	Sprites
	UISprite_TeamPhoto01	Sprites
	UISprite_TeamPhoto02	Sprites
	UISprite_TeamPhoto03	Sprites
	UISprite_WhosApp	Sprites
	WaterTower	Architecture				8
	WhispersOfTheDamned	SoundFX
	Window_Broken	Prop				2
	Window_Round	Prop				2
	Window_Square	Prop				2
	Workbench	Architecture				10

## Instellingen
Instellingen
	Projecten

	Categorie		Werknemer		1: Concept art
	Prop		Sasha		2: 2D Art		PRP_Name_001
	Architecture		Victoria		3: 3D Art		ARC_Name_001
	Environmental		Quinten		4: Unwrapping 3d models		NAT_Name_001
	Nature		Tom		5: Rigging		ALIV_Name_001
	Alive		Matthijs		6: Animating models		SPRT_Name_001
	Sprites		Aart-Jan		7: Sound		ANIM_Name_001
	Animation		Renzo		8: Scripts		SFX_Name_001
	Music		Gezamenlijk		9: Particles		BGM_Name_001
	SoundFX		Artists		0: Overig		PAR_Name_001
	ParticleFX		Programmers				SCR_Name_001
	Script		Yet to be assigned				SHDR_Name_001
	Shader		Leeg
	PostProcessing
	Overig