## Projecttracker
	Project AssetList, Anomaly		INSTELLINGEN	13 gamelab uren p/w	4 werkweken over	1 Polish week voor scene en presentatie		1D = 5P
				^52 uur total^		Alles moet hier af zijn, wordt niks nieuws gepland!
v	< O = Opermking, Zie meest rechtse balk
v						in punten		MoSCoW Method				?
	ProjectAssets	Categorie	Toegewezen aan	Geschat begin	Geschat einde	Geschatte hoeveelheid werk	SprintNmr.	Prioriteit	LEEG	Weeknummer	TrelloChecked	Implemented	Opmerkingen
	GameHandler	Script	Jan	28-11-2016	2-12-2016	12	0	Must Have		48	X
	Player_ComboScript	Script	Jan	28-11-2016	2-12-2016	6	0	Must Have
	HumanEnemy_00	3DModel	Niek	28-11-2016	2-12-2016	5	0	Must Have		48	X
	HumanEnemy_00	Texture	Niek	28-11-2016	2-12-2016	3	0	Must Have		48	X
	PlayerAttack_00	Animation	Niek	28-11-2016	2-12-2016	1	0	Must Have		48
	PlayerAttack_01	Animation	Niek	28-11-2016	2-12-2016	1	0	Must Have		48
	PlayerAttack_02	Animation	Niek	28-11-2016	2-12-2016	1	0	Must Have		48
	PlayerAttack_03	Animation	Niek	28-11-2016	2-12-2016	1	0	Must Have		48
	PlayerAttack_04	Animation	Niek	28-11-2016	2-12-2016	1	0	Must Have		48
	PlayerJump_00	Animation	Niek	28-11-2016	2-12-2016	1	0	Must Have
	CameraMovement	Script	Renzo	28-11-2016	2-12-2016	3	0	Must Have		48	X
	BossTokkie	3DModel	Sunray	28-11-2016	2-12-2016	4	0	Must Have
	BossTokkie	Rig	Sunray	28-11-2016	2-12-2016	1	0	Must Have
	BossTokkie	Texture	Sunray	28-11-2016	2-12-2016	3	0	Must Have
	MainChar	3DModel	Sunray	28-11-2016	2-12-2016	?	0	Must Have
	MainChar	Rig	Sunray	28-11-2016	2-12-2016	?	0	Must Have
	MainChar	Texture	Sunray	28-11-2016	2-12-2016	?	0	Must Have
	WeaponShortSword	3DModel	Sunray	28-11-2016	2-12-2016	1	0	Must Have
O	WeaponShortSword	Texture	Sunray	28-11-2016	2-12-2016	1	0	Must Have
	Ashtray	Prop	Quinten	28-2-2017	1-3-2017	1	1	Should Have
	Axe	Prop	Matthijs	2-3-2017	5-3-2017	3	1	Must Have
	Barn	Architecture	Aart-Jan	1-3-2017	9-3-2017	20	1	Must Have
	Barrel	Prop				1		Could Have
	Basement_CorkBoardWallmounted	Prop				1		Should Have
	Basement_Desk	Prop				4		Must Have
O	Basement_Newspaper	Prop				1		Could Have
	Basement_Pipes	Architecture				2		Could Have
	Basement_Staircase	Architecture				5		Must Have
	Bath	Prop				2		Could Have
	BearTrap	Prop				3		Should Have
	Bed	Prop				5		Could Have
	BeerBottle	Environmental				2		Could Have
	BicycleBell	Prop				2		Should Have
	Boiler	Environmental				10		Could Have
	Boltcutter	Prop				3		Should Have
	Book_Closed	Prop				1		Could Have
	Book_Open	Prop				2		Could Have
	Boots	Prop				2		Could Have
O	Briefcase	Prop				3		Must Have
	Briefcase_Notes	Prop				2		Must Have
	Broom	Prop				1		Could Have					WitchesBroom
O	CameraController	Script						Must Have
O	Candle	Environmental				2		Should Have
	Cellphone	Prop				7		Must Have
	Cellphone_Broken					4		Should Have
O	CellphoneCharger_Deskmounted					4		Must Have
O	Chain	Prop				1		Could Have
	Chair_00	Prop				3		Should Have
	Chair_01	Prop				3		Could Have
	Chandelier	Environmental				3		Could Have
	ChickenCoop	Environmental				5		Should Have
	Cleaver	Prop				4		Could Have
	Closet_wallmounted	Architecture				4		Should Have
	Clother_Shredded	Prop				5
	Clothes	Prop				4
	Coat Rack	Architecture				2
	ConfederateFlag	Environmental				1
	Container	Environmental				3
	CookingTimer	Prop				2
	Couch	Architecture				3
O	CraftingSystem	Script
	Crate	Prop				1
	Curtains	Architecture				4
	Door_00	Architecture				2
	Door_01	Architecture				2
	DOSComputer	Prop				4
	Douche	Prop				2
	Duck_Evil	Alive				10
?	DuckTape	Prop				1
O	EnemyBehaviour	Script
	EnemyVision	Script
	FalloutShelter	Architecture				5
	FarmSign	Environmental				2
	Feathers	Nature				2
	Fence_Steel	Prop				2
	Fence_SteelBroken	Prop				3
	Fence_Wood	Prop				2
	Fence_WoodBroken	Prop				3
	Fireplace	Architecture				4
	Flashlight	Prop				2
	Flashlight	Script
	FlowerDead_00	Nature				4
O	FlowerDead_01	Nature				4
	Freezer	Environmental				3
	Furnace	Environmental				3
O	GameManger	Script
	Gasmask	Prop				6
	GlassShattered	Environmental				2
	GUI	Script
	Hammer	Prop				2
	HangingBodies	Environmental				4
	HanginRope	Environmental				3
	Hay	Environmental				1
	HorseHoof_Rusty	Prop				1
O	House_Base	Architecture				30
	House_Room_00	Architecture				15
	House_Room_01	Architecture				15
	House_Room_02	Architecture				15
	House_Room_03	Architecture				15
	House_Room_04	Architecture				10
	House_Room_05	Architecture				10
	House_Room_06	Architecture				10
	House_Room_07	Architecture				10
	House_Room_08	Architecture				10
	Insanity	Script
	Insanity_BloodPool	Shader				1
	Insanity_Bloodspatter	Sprites				1
O	Insanity_DrippingBlood	Shader				1
	Insanity_Eyes	Prop				1
	Insanity_Fingers	Prop				2
	Insanity_PFX	ParticleFX				35							Moet nog uitbreiden hierop
	Insanity_Tentacles	Prop				3
	InventorySystem	Script
	Item(class)	Script
O	ItemDatabase	Script
	Jerrycan	Environmental				3
	Jochem	Shader				69
	Kitchen_Closet	Architecture				3
	Kitchen_Sink	Architecture				4
	Kitchen_Table	Architecture				3
	Kitchen_Tools	Prop				5
	Ladder	Prop				2
	LadderBroken	Prop				2
	Lamp_Hanging	Architecture				4
	Lamp_Standing	Architecture				4
	Lamp_WallMounted	Architecture				2
	Lantern	Prop				4
	Light(class)	Script
	LightManager	Script
	LightSwitch	Architecture				1
	Lockpick	Prop				2
	Mailbox	Prop				3
	MainCharacter	Alive				12							Alleen armen, of make Human???
	MainEnemy	Alive				30							Heeft nog een naam nodig
	Mais_crops	Nature				10
	MapNotes	Sprites				3
	Newspaper	Prop				1
	NoiseMaker	Prop				5
	NoiseMaker	Script
	Outhouse	Environmental				4
	Painting_00	Architecture				2
	Painting_01	Architecture				2
	Painting_02	Architecture				2
	Painting_03	Architecture				2
	Painting_04	Architecture				2
	PaperNotes	Prop				1
	Particle(class)	Script
	ParticleManager	Script
	Pencil	Prop				1
	PhoneUI	Sprites				20
	Piano	Prop				6
	Pitchfork	Prop				3
	Plank	Prop				1
	PlankBroken	Prop				1
	PlayerController	Script
	Plowing_Wagon	Environmental				5
	PowerGenerator	Environmental				10
	Rake	Prop				2
	Rat	Environmental				5
	RatHole	Architecture				1
	RatTrap	Environmental				2
	Rock_00	Environmental				2
	Rock_01	Environmental				2
	RockingChair	Prop				5
	Rope	Prop				3
	Rug	Environmental				4
	Rugsack					4
	Sadle					3
	Safe					3
	Saw					4
	ScrapMetal					3
	Screwdriver					2
	ScriptedEvents	Script
	Shotgun_Broken					7
	Sickle					3
	Sigars					1
	Silo	Architecture				7
	Sink					3
	Skybox	Script
	Skybox_00					3
	Skybox_01					3
	Skybox_02					3
	SoundManager	Script
	Staircase					10
	StartCables					2
	Table					2
	Table_Small					2
	Telephone_Wallmounted					4
	TelephonePole					2
	Terrain					15
	TimberBlocks					1
	Toilet					3
	Toolbelt					2
	Tractor	Prop				20
	TractorAccu					2
	Trashcan					1
	Tree_00	Nature				1
	Tree_01	Nature				1
	Tree_02	Nature				1
	TreeStump					1
	Truck	Prop				20
	Window_Broken					2
	Window_Round					2
	Window_Square					2
	Workbench					10
	WaterTower	Architecture				8

## Instellingen
Instellingen
	Projecten

	Categorie		Werknemer		1: Concept art
	Prop		Sasha		2: 2D Art		PRP_Name_001
	Architecture		Victoria		3: 3D Art		ARC_Name_001
	Environmental		Quinten		4: Unwrapping 3d models		NAT_Name_001
	Nature		Tom		5: Rigging		ALIV_Name_001
	Alive		Matthijs		6: Animating models		SPRT_Name_001
	Sprites		Aart-Jan		7: Sound		ANIM_Name_001
	Animation		Renzo		8: Scripts		SFX_Name_001
	Music		Gezamenlijk		9: Particles		BGM_Name_001
	SoundFX		Artists		0: Overig		PAR_Name_001
	ParticleFX		Programmers				SCR_Name_001
	Script		Yet to be assigned				SHDR_Name_001
	Shader		Leeg
	PostProcessing
	Overig