## Projecttracker
Project AssetList, Anomaly		INSTELLINGEN			1 Polish week voor scene en presentatie		1D = 3P		18 Gamelab uren p/w
					Alles moet hier af zijn, wordt niks nieuws gepland!		1D = 5P

	v = Opermking, Zie meest rechtse balk					in punten	MoSCoW Method				?
v	ProjectAssets	Categorie	Toegewezen aan	Geschat begin	Geschat einde	Geschatte hoeveelheid werk	SprintNmr.	Prioriteit	LEEG	Weeknummer	TrelloChecked	Implemented	Opmerkingen
	GameHandler	Script	Jan	28-11-2016	2-12-2016	12	0	Must Have		48	X
	HumanEnemy_00	3DModel	Niek	28-11-2016	2-12-2016	5	0	Must Have		48	X
	HumanEnemy_00	Texture	Niek	28-11-2016	2-12-2016	3	0	Must Have		48	X
	Item(class)	Script				5	1	Must Have
O	Basement_Staircase	Architecture				5	1	Must Have
	Briefcase	Prop				3	1	Must Have
	CameraController	Script	Sasha			10	1	Must Have
	Cellphone	Prop				7	1	Must Have
	CellphoneCharger_Deskmounted	Prop				4	1	Must Have
	CameraMovement	Script	Renzo	28-11-2016	2-12-2016	3	0	Must Have		48	X
	Character_Arms	Alive				2	1	Must Have
	House_Base	Architecture				30	1	Must Have
	House_Basement	Architecture				15	1	Must Have
	PlayerController	Script	Sasha			10	1	Must Have
	PowerGenerator	Environmental	Matthijs			10	1	Must Have
	EdgePortal	Script	Renzo			15	1	Must Have
	Briefcase_Notes	Prop				2	1	Must Have
	Workbench	Prop				10	1	Should Have
O!	ScriptedEvents	Script				5	2	Must Have					Moeten zeer nodig besproken worden!
	House_Room_01	Architecture				15	2	Must Have
	House_Room_02	Architecture				15	2	Must Have
	House_Room_03	Architecture				15	2	Must Have
	EnemyBehaviour	Script				10	2	Must Have
	EnemyVision	Script				10	2	Must Have
	GameManger	Script				10	2	Must Have
	ItemDatabase	Script				5	2	Must Have
	InventorySystem	Script				GUI	1	Must Have
O	CraftRecipeBlueprint_Generator	Script				1	3	Must Have					Gedeelte van het script wat ervoor zorgt dat dit het doet
	CraftMaterial_TractorBattery	Prop				3	3	Must Have
O	CraftMaterial_Gasoline	Prop				3	3	Must Have					The Jerrycan i presume
	CraftMaterial_StartCables	Prop				2	3	Must Have
	GUI	Script				21	3	Must Have
	SoundManager	Script				5	3	Must Have
	CraftingSystem	Script	Renzo			15	1t2	Must Have
	Terrain	Environmental				25	1t3	Must Have
O	MainEnemy	Alive				30	1t4	Must Have					Heeft nog een naam nodig
	Door	Architecture				2	1	Must Have
	Barn	Architecture				20	1	Should Have
	CharacterAnimation_ArmsWalking	Animation				6	2	Should Have
	UISprite_SuitCaseNote00	Sprites				1	1	Should Have
O	Insanity_PFX	ParticleFX				35	2	Should Have					Moet nog uitbreiden hierop
O	Lantern	Script				2	3	Should Have					Duration on it, perhaps?
	Basement_CorkBoardWallmounted	Prop				1	3	Should Have
	CharacterAnimation_ArmsIdle	Animation				6	3	Should Have
O	Flashlight	Prop				2	3	Should Have
	Rock_00	Environmental				2	3	Should Have
	UISprite_SuitCaseNote01	Sprites				1	1	Should Have
	UISprite_SuitCaseNote02	Sprites				1	2	Should Have
	Basement_Desk	Prop				4	3	Should Have
O	Jerrycan	Environmental				3	3	Should Have					Misschien is dit een requirement om de gasoline mee te kunnen nemen?
	CharacterAnimation_Interact	Animation				3	3	Should Have
	Mais_crops	Nature				5	3	Should Have
	PhoneUI	Sprites				20	5	Should Have
	UISprite_BatteryStatus00	Sprites					5	Should Have
	UISprite_BatteryStatus01	Sprites					5	Should Have
	UISprite_BatteryStatus02	Sprites					5	Should Have
O	QuickSelectApp	Script				5	7	Should Have					Quickselect, een item met een assignable hotkey
	Tractor	Environmental				20	4+	Should Have
	CraftRecipeBlueprint_Lantern	Sprites					5+	Should Have
	Duck_Evil	Alive				10	5+	Should Have
	UISprite_SuitCaseNote03	Sprites				1		Should Have
	UISprite_SuitCaseNote04	Sprites				1		Should Have
	BearTrap	Prop				3		Should Have
	CharacterAnimation_ArmsRunning	Animation				6		Should Have
	CharacterAnimation_DeathByAlien	Animation				9		Should Have
	CharacterAnimation_Insanity	Animation				6		Should Have
	CraftMaterial_ScrapMetal	Prop				3		Should Have
	House_Room_04	Architecture				10		Should Have
	House_Room_05	Architecture				10		Should Have
	House_Room_06	Architecture				10		Should Have
	House_Room_07	Architecture				10		Should Have
	House_Room_08	Architecture				10		Should Have
	Insanity_Eyes	Prop				1		Should Have
	Insanity_Tentacles	Prop				3		Should Have
	Lantern	Prop				4		Should Have
	Painting_00	Architecture				2		Should Have
	Silo	Architecture				7		Should Have
	Skybox_00	Overig				3		Should Have
	Staircase_1stFloor	Prop				10		Should Have
	Tree_00	Nature				1		Should Have
	WaterTower	Architecture				8		Should Have
	AnomalySFX_00	SoundFX				3		Should Have
	AnomalySFX_01	SoundFX				3		Should Have
	BackGroundAmbience	SoundFX				7		Should Have
	CraftRecipe_Lantern	Sprites				2		Should Have
	DoorOpening	Animation				2		Should Have
	EnemyFootsteps	SoundFX				2		Should Have
	Insanity	Script				15		Should Have
	Particle(class)	Script				2		Should Have
O	ParticleManager	Script				2		Should Have					Werkt het met occlusion culling
	Skybox	Script				5		Should Have
	UISprite_TeamPhoto00	Sprites				2		Should Have
	Character_Body	Alive				2	1	Could Have
	Axe	Prop	Matthijs			3	1	Could Have
	Fence_Steel	Prop				2		Could Have
	Fence_SteelBroken	Prop				3		Could Have
	CraftRecipeBlueprint_Generator	Sprites						Could Have
	Basement_Pipes	Prop				2		Could Have
	CharacterAnimation_Crouching	Animation						Could Have
	CharacterAnimation_Jumping	Animation						Could Have
	CharacterAnimation_Suicide	Animation						Could Have
	Closet_wallmounted	Prop				4		Could Have
	CraftRecipeBlueprint_MakeShiftAxe	Sprites						Could Have
	BeerBottle	Environmental				2		Could Have
	Boiler	Environmental				10		Could Have
	Chandelier	Environmental				3		Could Have
	Insanity_Fingers	Prop				2		Could Have
	PlayerPanicking	Animation						Could Have
	AnomalySFX_02	SoundFX						Could Have
	Light(class)	Script				2		Could Have
	EnemyRoar00	SoundFX						Could Have
O	LightManager	Script				2		Could Have					Werkt het met occlusion culling
	ForeGroundAmbience	SoundFX						Could Have
	Barrel	Prop				1		Could Have
	Basement_Newspaper	Prop				1		Could Have
	Bath	Prop				2		Could Have
	Bed	Prop				5		Could Have
	Book_Closed	Prop				1		Could Have
	Book_Open	Prop				2		Could Have
	Boots	Prop				2		Could Have
	Broom	Prop				1		Could Have					WitchesBroom
	UISprite_Gallery	Sprites						Could Have
O	UISprite_GalleryFolders	Sprites						Could Have
	Chain	Prop				1		Could Have
	UISprite_HeartMeter	Sprites						Could Have
	Chair_01	Prop				3		Could Have
	Cleaver	Prop				4		Could Have
	UISprite_Notebook	Sprites						Could Have
	UISprite_Settings	Sprites						Could Have
	UISprite_SuitCaseNote05	Sprites						Could Have
	UISprite_SuitCaseNote06	Sprites						Could Have
	UISprite_SuitCaseNote07	Sprites						Could Have
	UISprite_SuitCaseNote08	Sprites						Could Have
	BicycleBell	Prop				2		Could Have
	ChickenCoop	Environmental				5		Could Have
	Clothes	Prop				4		Could Have
	Container	Environmental				3		Could Have
O	Couch	Prop				3		Could Have
	CraftMaterial_CookingTimer	Prop						Could Have
	CraftMaterial_DuctTape	Prop						Could Have
	CraftMaterial_Nuts&Bolts	Prop						Could Have
	CraftMaterial_Rope	Prop						Could Have
	CraftMaterial_WoodenPlanks	Prop						Could Have
	CraftRecipeBlueprint_BearTrap	Sprites						Could Have
	CraftRecipeBlueprint_LockPick	Sprites						Could Have
	CraftRecipeBlueprint_NoiseMaker	Sprites						Could Have
	Door_01	Prop				2		Could Have
	DuckTape	Prop				1		Could Have
	FalloutShelter	Architecture				5		Could Have
	FarmSign	Environmental				2		Could Have
	Feathers	Nature				2		Could Have
	Fence_Wood	Prop				2		Could Have
	Fence_WoodBroken	Prop				3		Could Have
	Fireplace	Prop				4		Could Have
	FlowerDead_00	Nature				4		Could Have
	FlowerDead_01	Nature				4		Could Have
	Freezer	Environmental				3		Could Have
	Furnace	Environmental				3		Could Have
	Gasmask	Prop				6		Could Have
	GlassShattered	Environmental				2		Could Have
O	Hammer	Prop				2		Could Have
	HangingBodies	Environmental				4		Could Have
	HanginRope	Environmental				3		Could Have
	Hay	Environmental				1		Could Have
	HorseHoof_Rusty	Prop				1		Could Have
	Kitchen_Closet	Prop				3		Could Have
	Kitchen_Sink	Prop				4		Could Have
	Kitchen_Table	Prop				3		Could Have
	Kitchen_Tools	Prop				5		Could Have
	Ladder	Prop				2		Could Have
	LadderBroken	Prop				2		Could Have
	Lamp_Hanging	Prop				4		Could Have
	Lamp_Standing	Prop				4		Could Have
	Lamp_WallMounted	Prop				2		Could Have
	LightSwitch	Prop				1		Could Have
	Lockpick	Prop				2		Could Have
	LooneyTunes_Intro	Animation						Could Have
	Mailbox	Prop				3		Could Have
	Newspaper	Prop				1		Could Have
	NoiseMaker	Prop				5		Could Have
	Outhouse	Environmental				4		Could Have
	Painting_01	Prop				2		Could Have
	Painting_02	Prop				2		Could Have
	Painting_03	Prop				2		Could Have
	Painting_04	Prop				2		Could Have
	PaperNotes	Prop				1		Could Have
O	Pencil	Prop				1		Could Have
	Piano	Prop				6		Could Have
	Pitchfork	Prop				3		Could Have
	Plank	Prop				1		Could Have
	PlankBroken	Prop				1		Could Have
	PlayerBreathing	ParticleFX						Could Have
	PlayerFootsteps	ParticleFX						Could Have
	PlayerJumpLanding	ParticleFX						Could Have
	Plowing_Wagon	Environmental				5		Could Have
	Rake	Prop				2		Could Have
	Rat	Environmental				5		Could Have
	RatHole	Prop				1		Could Have
	RatTrap	Environmental				2		Could Have
	Rock_01	Environmental				2		Could Have
	RockingChair	Prop				5		Could Have
	Rope	Prop				3		Could Have
	Rug	Environmental				4		Could Have
O	Rugsack	Prop				4		Could Have					Increased dit je inventory?
	Rustle_Bushes	Animation						Could Have
	Rustle_Trash	Animation						Could Have
	Sadle	Prop				3		Could Have
O	Safe	Prop				3		Could Have					Een kluis
	Jochem	Overig				69		Could Have
	Saw	Prop				4		Could Have
	Screwdriver	Prop				2		Could Have
	Shotgun_Broken	Prop				7		Could Have
	Sickle	Prop				3		Could Have
	Sigars	Prop				1		Could Have
	Sink	Prop				3		Could Have
	Skybox_01	Overig				3		Could Have
	Skybox_02	Overig				3		Could Have
	Swing	Prop						Could Have					Schommel
	Table	Prop				2		Could Have
	Table_Small	Prop				2		Could Have
	Telephone_Wallmounted	Prop				4		Could Have
	TelephonePole	Prop				2		Could Have
	TimberBlocks	Prop				1		Could Have
	Toilet	Prop				3		Could Have
O	Toolbelt	Prop				2		Could Have					Werdt dit ook gebruikt?
	Tree_01	Nature				1		Could Have
	Tree_02	Nature				1		Could Have
	TreeStump	Nature				1		Could Have
	AnomalySFX_03	SoundFX						Could Have
	AnomalySFX_04	SoundFX						Could Have
	AnomalySFX_05	SoundFX						Could Have
	AnomalySFX_06	SoundFX						Could Have
	AnomalySFX_07	SoundFX						Could Have
	AnomalySFX_08	SoundFX						Could Have
	AnomalySFX_09	SoundFX						Could Have
	Birds_Fladdering	SoundFX						Could Have
	BirdsSpooked	SoundFX						Could Have
	CellPhone_BuzzSFX	SoundFX						Could Have
	CellPhone_ChargingSFX	SoundFX						Could Have
O	CellPhone_RealLifeClock	Script						Could Have					Kunnen wellicht in een algeheel phone script
	Cellphone_Ringtone	SoundFX						Could Have
	CellPhone_TouchSound	SoundFX						Could Have
	CraftMaterial_CarBattery	Sprites						Could Have
	CraftMaterial_Gasoline	Sprites						Could Have
	CraftMaterial_ScrapMetal	Sprites						Could Have
	CraftMaterial_StartCables	Sprites						Could Have
	CraftRecipe_LockPick	Sprites						Could Have
O	CraftRecipe_MakeShiftAxe	Sprites						Could Have
	CraftRecipe_NoiseMaker	Sprites						Could Have
	DrippingWater	SoundFX						Could Have
	Duck_Qwuack	SoundFX						Could Have
	EnemyBreathing	SoundFX						Could Have
	EnemyRoar01	SoundFX						Could Have
	Rustle_Bushes	SoundFX						Could Have
	Rustle_Trash	SoundFX						Could Have
	Gramaphone_Tune	SoundFX						Could Have
	Gramaphone_TuneWithScreeches	SoundFX						Could Have
	GrandFatherClock_OnHourBong	SoundFX						Could Have
	GrandFatherClock_Ticking	SoundFX						Could Have
	HeadBobbing	Script						Could Have
	Insanity_BloodPool	Shader				1		Could Have
	Insanity_Bloodspatter	Sprites				1		Could Have
	Insanity_DrippingBlood	Shader				1		Could Have
	InsanityUndertone	SoundFX						Could Have
	Intro_CutScene	SoundFX						Could Have
O	Lantern	Script						Could Have					Duration on it, perhaps?
	LooneyTunes_Intro	SoundFX						Could Have
	MapNotes	Sprites				3		Could Have
	NoiseMaker	Script						Could Have
	NoiseMaker_Charging	SoundFX						Could Have
	NoiseMaker_InEffect	SoundFX						Could Have
	PianoTune_00	SoundFX						Could Have
	PianoTune_01	SoundFX						Could Have
	PlayerBreathing	SoundFX						Could Have
	PlayerCrouchFootsteps	SoundFX						Could Have					Kunnen dit normale footsteps niet zijn? Perhaps slomer en gedempt ofso
	PlayerDeathcries	SoundFX						Could Have
	PlayerFootsteps	SoundFX						Could Have
	PlayerJumpLanding	SoundFX						Could Have
	PlayerPanicking	SoundFX						Could Have
	Rats	SoundFX						Could Have
	Ravens	SoundFX						Could Have					Verschil van de vogels? - is deze overbodig?
	SqueakyDoor	SoundFX						Could Have
	SqueekingWood	SoundFX						Could Have
	TelevisionStatic	Shader						Could Have
	Tom&Jerry_intro	SoundFX						Could Have
	Trashcan	Prop				1		Could Have
	Truck	Prop				20		Could Have
	UISprite_Background01	Sprites						Could Have
	UISprite_Background02	Sprites						Could Have
	UISprite_Background03	Sprites						Could Have
	UISprite_Background04	Sprites						Could Have
	UISprite_BarnPhoto	Sprites						Could Have
O	UISprite_DuckHunt	Sprites						Could Have
	UISprite_FlashLigt	Sprites						Could Have
	UISprite_HousePhoto	Sprites						Could Have
	UISprite_KidOnSwing	Sprites						Could Have
	UISprite_KidOnSwingHeadless	Sprites						Could Have
	UISprite_MapApp	Sprites						Could Have
	UISprite_PhoneBackground	Sprites						Could Have
	UISprite_SuitCaseNote09	Sprites						Could Have
	UISprite_SuitCaseNote10	Sprites						Could Have
	UISprite_SuitCaseNote11	Sprites						Could Have
	UISprite_SuitCaseNote12	Sprites						Could Have
	UISprite_SuitCaseNote13	Sprites						Could Have
	UISprite_SuitCaseNote14	Sprites						Could Have
	UISprite_TeamPhoto01	Sprites						Could Have
	UISprite_TeamPhoto02	Sprites						Could Have
	UISprite_TeamPhoto03	Sprites						Could Have
	UISprite_WhosApp	Sprites						Could Have
	WhispersOfTheDamned	SoundFX						Could Have
	Window_Broken	Prop				2		Could Have
	Window_Round	Prop				2		Could Have
	Window_Square	Prop				2		Could Have
	Crate	Prop				1		Could Have
	Ashtray	Prop	Quinten			1	1	Would Have
	BirdsSpooked	ParticleFX						Would Have
	Candle	Environmental				2		Would Have
	Cellphone_Broken	Prop				4		Would Have
	Chair_00	Prop				3		Would Have
	CharacterAnimation_Suicide2	Animation						Would Have
	Clothes_Shredded	Prop				5		Would Have
	Coat Rack	Prop				2		Would Have
	ConfederateFlag	Environmental				1		Would Have
O	Curtains	Prop				4		Would Have
	DOSComputer	Prop				4		Would Have
	Douche	Prop				2		Would Have
	Boltcutter	Prop				3		Would Have
O	CellPhone_ReskinnnerApp	Script						Would Have					Kunnen wellicht in een algeheel phone script
	CraftMaterial_CookingTimer	Sprites						Would Have
	CraftMaterial_DuctTape	Sprites						Would Have
	CraftMaterial_Nuts&Bolts	Sprites						Would Have
	CraftMaterial_Rope	Sprites						Would Have
	CraftMaterial_WoodenPlanks	Sprites						Would Have
	CraftRecipe_BearTrap	Sprites						Would Have
O	MainCharacter	Alive				12							Alleen armen, of make Human???

## Instellingen
Instellingen
	Projecten

	Categorie		Werknemer		1: Concept art
	Prop		Sasha		2: 2D Art		PRP_Name_001
	Architecture		Victoria		3: 3D Art		ARC_Name_001
	Environmental		Quinten		4: Unwrapping 3d models		NAT_Name_001
	Nature		Tom		5: Rigging		ALIV_Name_001
	Alive		Matthijs		6: Animating models		SPRT_Name_001
	Sprites		Aart-Jan		7: Sound		ANIM_Name_001
	Animation		Renzo		8: Scripts		SFX_Name_001
	Music		Gezamenlijk		9: Particles		BGM_Name_001
	SoundFX		Artists		0: Overig		PAR_Name_001
	ParticleFX		Programmers				SCR_Name_001
	Script		Yet to be assigned				SHDR_Name_001
	Shader		Leeg
	PostProcessing
	Overig