## Projecttracker
	Projecttracker, Xeroderma		INSTELLINGEN	13 gamelab uren p/w	4 werkweken over	1 Polish week voor scene en presentatie		1D = 5P
				^52 uur total^		Alles moet hier af zijn, wordt niks nieuws gepland!
v	< O = Opermking, Zie meest rechtse balk
v						in uren		MoSCoW Method				?
	ProjectAssets	Categorie	Toegewezen aan	Geschat begin	Geschat einde	Geschatte hoeveelheid werk	SprintNmr.	Prioriteit	LEEG	Weeknummer	IsDone	Implemented	Opmerkingen
	Axe	Prop				3
	Barn	Architecture				20
	Barrel	Prop				1
	BeerBottle	Prop				2
	Broom	Prop				1							WitchesBroom
	Chair_00					3
	Chair_01					3
	Chandelier					3
	Couch					3
	Crate					1
	Door_00	Architecture				2
	Door_01	Architecture				2
	DuckTape					1
	Fence_Steel	Prop				2
	Fence_SteelBroken	Prop				3
	Fence_Wood	Prop				2
	Fence_WoodBroken	Prop				3
	FlowerDead_00					4
	FlowerDead_01					4
	GlassShattered					2
O	Hammer					2
	Hay					1
	House_Base	Architecture				30
	House_Room_00	Architecture				15
	House_Room_01	Architecture				15
	House_Room_02	Architecture				15
	House_Room_03	Architecture				15
	House_Room_04	Architecture				10
	House_Room_05	Architecture				10
	House_Room_06	Architecture				10
	House_Room_07	Architecture				10
	House_Room_08	Architecture				10
	Kitchen_Sink					4
	Kitchen_Table					3
	Ladder					2
	LadderBroken					2
	Lamp_WallMounted	Prop				2
	Mailbox					3
O	MainCharacter					12							Alleen armen, of make Human???
	MainEnemy	Alive				30							Heeft nog een naam nodig
	Newspaper					1
	Painting_00					2
	Painting_01					2
	Painting_02					2
O	Painting_03					2
	Painting_04					2
	Piano					6
	Pitchfork					3
	Plank					1
	PlankBroken					1
	Rock_00					2
	Rock_01					2
	Rope					3
	Saw					4
	ScrapMetal					3
	Screwdriver					2
	Silo	Architecture				7
	Staircase					10
	Table					2
	Table_Small					2
	Tractor	Prop				20
	Trashcan					1
	Tree_00	Nature				1
	Tree_01	Nature				1
	Tree_02	Nature				1
	TreeStump					1
	Truck	Prop				20
	Window_Broken					2
	Window_Round					2
	Window_Square					2
	Workbench					10
	Lamp_Standing					4
	Lamp_Hanging					4
	Kitchen_Closet					3
	Kitchen_Tools					5
	Furnace					3
	Fireplace					4
	LightSwitch					1
	Bath					2
	Toilet					3
	Douche					2
	Sink					3
	Curtains					4
	Sigars					1
	Ashtray					1
	Rat					5
	RatTrap					2
	RatHole					1
	Duck_Evil					10
	Shotgun_Broken					7
	Boiler					10
	BearTrap					3
	Mais_crops					10
	HorseHoof_Rust					1
	Plowing_Wagon					5
	Chain					1
	FarmSign					2
	ChickenCoop					5
	Sickle					3
	Rake					2
	Bed					5
	Closet_wallmounted					4
	Basement_Staircase					5
	Basement_Pipes					2
	Basement_Desk					4
	Basement_CorkBoardWallmounted					1
	Basement_Newspaper					1
	Book_Closed					1
	Book_Open					2
	PaperNotes					1
	Pencil					1
	Cellphone_Broken					4
	Telephone_Wallmounted					4
	CellphoneCharger_Deskmounted					4
	Cellphone					7
	RockingChair					5
	PowerGenerator					10
	Jerrycan					3
	Coat Rack					2
	TractorAccu					2
	StartCables					2
	ConfederateFlag					1
	Gasmask					6
	Cleaver					4
	Insanity_Bloodspatter					1
	Sadle					3
	Jochem					69
	Terrain					15
	FalloutShelter					5
	Outhouse					4
	Briefcase					3
	Briefcase_Notes					2
	MapNotes					3
	Skybox_00					3
	Skybox_01					3
	Skybox_02					3
	Feathers					2
	Clothes					4
	Clother_Shredded					5
	TimberBlocks					1
	Insanity_Eyes					1
	Insanity_Fingers					2
	Insanity_DrippingBlood					1
	Insanity_BloodPool					1
	Insanity_Tentacles					3
O	Insanity_PFX					35							Moet nog uitbreiden hierop
	PhoneUI					20
	Rug					4
	Container					3
	Boots					2
	HangingBodies					4
	HanginRope					3
	Freezer					3
	Flashlight					2
	Lantern					4
	Toolbelt					2
	Lockpick					2
	Safe					3
	Candle					2
	DOSComputer					4
	NoiseMaker					5
	BicycleBell					2
	CookingTimer					2
	Boltcutter					3
	TelephonePole					2
	Rugsack					4

## Instellingen
Instellingen
	Projecten

	Categorie		Werknemer		1: Concept art
	Prop		Sash		2: 2D Art		PRP_Name_001
	Architecture		Victory		3: 3D Art		ARC_Name_001
	Environmental		Quintescence		4: Unwrapping 3d models		NAT_Name_001
	Nature		Tomtom		5: Rigging		ALIV_Name_001
	Alive		Mattizo		6: Animating models		SPRT_Name_001
	Sprites		Earth-Jan		7: Sound		ANIM_Name_001
	Animation		RenRen		8: Scripts		SFX_Name_001
	Music		Gezamenlijk		9: Particles		BGM_Name_001
	SoundFX		Artists		0: Overig		PAR_Name_001
	ParticleFX		Programmers				SCR_Name_001
	Script		Yet to be assigned				SHDR_Name_001
	Shader		Leeg
	PostProcessing
	Overig