## Projecttracker
	Projecttracker, Xeroderma		INSTELLINGEN	13 gamelab uren p/w	4 werkweken over	1 Polish week voor scene en presentatie		1D = 5P
				^52 uur total^		Alles moet hier af zijn, wordt niks nieuws gepland!
v	< O = Opermking, Zie meest rechtse balk
v						in uren		MoSCoW Method				?
	ProjectAssets	Categorie	Toegewezen aan	Geschat begin	Geschat einde	Geschatte hoeveelheid werk	SprintNmr.	Prioriteit	LEEG	Weeknummer	IsDone	Implemented	Opmerkingen
	Axe	Prop				3
	Barn	Architecture				20
	Barrel	Prop				1
	BeerBottle	Prop				2
	Broom	Prop				1							WitchesBroom
	Chair_00					3
	Chair_01					3
	Chandelier					3
	Couch					3
	Crate					1
	Door_00	Architecture				2
	Door_01	Architecture				2
	DuckTape					1
	Fence_Steel	Prop				2
	Fence_SteelBroken	Prop				3
	Fence_Wood	Prop				2
	Fence_WoodBroken	Prop				3
	FlowerDead_00					4
	FlowerDead_01					4
	GlassShattered					2
O	Hammer					2
	Hay					1
	House_Base	Architecture				30
	House_Room_00	Architecture				15
	House_Room_01	Architecture				15
	House_Room_02	Architecture				15
	House_Room_03	Architecture				15
	House_Room_04	Architecture				10
	House_Room_05	Architecture				10
	House_Room_06	Architecture				10
	House_Room_07	Architecture				10
	House_Room_08	Architecture				10
	Kitchen_Sink					4
	Kitchen_Table					3
	Ladder					2
	LadderBroken					2
	Lamp_WallMounted	Prop				2
	Mailbox					3
O	MainCharacter					12							Alleen armen, of make Human???
	MainEnemy	Alive				30							Heeft nog een naam nodig
	Newspaper					1
	Painting_00					2
	Painting_01					2
	Painting_02					2
O	Painting_03					2
	Painting_04					2
	Piano					6
	Pitchfork					3
	Plank					1
	PlankBroken					1
	Rock_00					2
	Rock_01					2
	Rope					3
	Saw					4
	ScrapMetal					3
	Screwdriver					2
	Silo	Architecture				7
	Staircase					10
	Table					2
	Table_Small					2
	Tractor	Prop				20
	Trashcan					1
	Tree_00	Nature				1
	Tree_01	Nature				1
	Tree_02	Nature				1
	TreeStump					1
	Truck	Prop				20
	Window_Broken					2
	Window_Round					2
	Window_Square					2
	Workbench					10
	Lamp_Standing					4
	Lamp_Hanging					4
	Kitchen_Closet					3
	Kitchen_Tools					5
	Furnace					3
	Fireplace					4
	LightSwitch					1
	Bath					2
	Toilet					3
	Douche					2
	Sink					3
	Curtains					4
	Sigars					1
	Ashtray					1
	Rat					5
	RatTrap					2
	RatHole					1
	Duck_Evil					10
	Shotgun_Broken					7
	Boiler					10
	BearTrap					3
	Mais_crops					10
	HorseHoof_Rust					1
	Plowing_Wagon					5
	Chain					1
	FarmSign					2
	ChickenCoop					5
	Sickle					3
	Rake					2
	Bed					5
	Closet_wallmounted					4
	Basement_Staircase					5
	Basement_Pipes					2
	Basement_Desk					4
	Basement_CorkBoardWallmounted					1
	Basement_Newspaper					1
	Book_Closed					1
	Book_Open					2
	PaperNotes					1
	Pencil					1
	Cellphone_Broken					4
	Telephone_Wallmounted					4
	CellphoneCharger_Deskmounted					4
	Cellphone					7
	RockingChair					5
	PowerGenerator					10
	Jerrycan					3
	Coat Rack					2
	TractorAccu					2
	StartCables					2
	ConfederateFlag					1
	Gasmask					6
	Cleaver					4
	Insanity_Bloodspatter					1
	Sadle					3
	Jochem					69
	Terrain					15
	FalloutShelter					5
	Outhouse					4
	Briefcase					3
	Briefcase_Notes					2
	MapNotes					3
	Skybox_00					3
	Skybox_01					3
	Skybox_02					3
	Feathers					2
	Clothes					4
	Clother_Shredded					5
	TimberBlocks					1
	Insanity_Eyes					1
	Insanity_Fingers					2
	Insanity_DrippingBlood					1
	Insanity_BloodPool					1
	Insanity_Tentacles					3
O	Insanity_PFX					35							Moet nog uitbreiden hierop
	PhoneUI					20
	Rug					4
	Container					3
	Boots					2
	HangingBodies					4
	HanginRope					3
	Freezer					3
	Flashlight					2
	Lantern					4
	Toolbelt					2
	Lockpick					2
	Safe					3
	Candle					2
	DOSComputer					4
	NoiseMaker					5
	BicycleBell					2
	CookingTimer					2
	Boltcutter					3
	TelephonePole					2
	Rugsack					4

	GameManger	Script
	ScriptedEvents	Script
	Insanity	Script
	GUI	Script
	SoundManager	Script
	LightManager	Script
	Light(class)	Script
	InventorySystem	Script
	ItemDatabase	Script
	Item(class)	Script
	PlayerController	Script
	CameraController	Script
	CraftingSystem	Script
	ParticleManager	Script
	Particle(class)	Script
	EnemyBehaviour	Script
	EnemyVision	Script
	Skybox	Script
	NoiseMaker	Script
	Flashlight	Script

## Instellingen
Instellingen
	Projecten

	Categorie		Werknemer		1: Concept art
	Prop		Sash		2: 2D Art		PRP_Name_001
	Architecture		Victory		3: 3D Art		ARC_Name_001
	Environmental		Quintescence		4: Unwrapping 3d models		NAT_Name_001
	Nature		Tomtom		5: Rigging		ALIV_Name_001
	Alive		Mattizo		6: Animating models		SPRT_Name_001
	Sprites		Earth-Jan		7: Sound		ANIM_Name_001
	Animation		RenRen		8: Scripts		SFX_Name_001
	Music		Gezamenlijk		9: Particles		BGM_Name_001
	SoundFX		Artists		0: Overig		PAR_Name_001
	ParticleFX		Programmers				SCR_Name_001
	Script		Yet to be assigned				SHDR_Name_001
	Shader		Leeg
	PostProcessing
	Overig